## Accessibility Plan
Precision Nutrition Accessibility Plan: 2021 - 2023
Goal | Status | Targeted Completion Date | Actual Completion Date
Accessibility gap assessment completed | Complete | 2021-02-01 | 2021-03-01
Accessibility testing framework rolled out in CI | Complete | 2021-06-01 | 2021-05-01
Accessibility plugins added to CMS | Complete | 2021-06-01 | 2021-04-01
Roles created for accessibility | Complete | 2021-06-01 | 2021-04-01
Accessibility policy rolled out | Complete | 2021-06-01 | 2021-05-01
2-year accessibility plan completed | Complete | 2021-06-01 | 2021-06-01
Accessibility governance proposals at GCC and TG&D accepted | Complete | 2021-06-01 | 2021-06-01
Template changes implemented in CMS | Partial | 2021-06-01 | 2021-06-01
Accessibility and supports language added to Careers page | Complete | 2021-06-01 | 2021-06-01
Sales pages on site perceivable and operable | Complete | 2021-06-01 | 2021-06-01
Accessible redesign of products completed | Complete | 2021-06-01 | 2021-06-01
Policy requiring all new content and products to be WCAG 2.0 AA compliant before release | Completed | 2021-06-01 | 2021-06-01
Top 200 blog posts edited for accessibility compliance | Partial | 2021-12-01
All free calculators perceivable and operable | Pending | 2021-12-01
Accessibility designs implemented across all products | Partial | 2022-06-01
QA tests for WCAG 2.0 AA before major releases (catching anything CI tests don't catch) | Pending | 2022-12-01
Top 1000 blog posts edited for accessibility compliance | Pending | 2022-12-01
All blog posts edited for accessibility compliance | Pending | 2023-12-01
All coaching and certification content accessible | Ongoing
Have questions? Or feedback? We want to hear from you. Please contact us by email at accessibility@precisionnutrition.com, or by phone at 1-877-660-6464 (US & Canada).